## How to use
Requirements Traceability Matrix
A free template from requirementsfirst.com. Three linked tables, coverage calculated for you.
How it works
1. Business Reqs: one row per outcome the business wants. Fill in the cream columns.
2. Functional Reqs: one row per thing the system must do. Pick the BR it serves from the dropdown (and a second BR if it serves two).
3. Test Cases: one row per test. Pick the FR it proves and set the result to Not run, Pass or Fail.
Blue-grey columns are formulas. Do not type in them. Each sheet has 100 rows ready; copy the last row down for more.
Coverage (Functional Reqs)
No tests: nothing linked. Failing: any linked test failed. Not run yet: some tests not run. Passing: every linked test passed.
Trace status (Business Reqs)
Not traced: no FRs linked. Failing: any FR is failing. Gaps: any FR has no tests or untested ones. Fully tested: everything beneath it passes.
The example
The rows already filled in are a synthetic refund portal project: BR-1 is Fully tested, BR-2 is Failing, BR-3 has Gaps. Delete the example rows (cream columns only) when you start your own.
Read the full guide
https://requirementsfirst.com/posts/requirements-traceability-matrix-template/
Prefer Notion? The same template as three linked databases: https://requirementsfirst.gumroad.com/l/bkgdtg

## Business Reqs
BR ID | Business requirement | Objective it serves | Priority | Signs off | FRs linked | FRs failing | FRs with gaps | Trace status
BR-1 | Customers can get a refund without contacting support | Cut refund-related support contacts | Must | Priya, Head of Customer Support
BR-2 | Refunds are paid out within one business day | Faster refunds, fewer chasers | Must | David, Finance Controller
BR-3 | Finance can audit every refund | Pass the year-end refund audit | Should | Rahul, Compliance Manager

## Functional Reqs
FR ID | Functional requirement | Serves BR | Also serves BR (optional) | Acceptance criteria | Build status | Tests linked | Tests passed | Tests failed | Coverage
FR-1 | Customer can start a refund from their order history page | BR-1 |  | Given a delivered order under 30 days old, when the customer selects Refund, then a refund request is created and confirmed on screen | Built
FR-2 | Refunds under 50 dollars are approved automatically | BR-2 |  | Given a request under 50 dollars, when it is submitted, then it is approved with no manual step | In progress
FR-3 | Approved refunds are sent to the payment gateway within one hour | BR-2 |  | Given an approved refund, when one hour has passed, then the gateway has accepted the payout | Built
FR-4 | Every refund decision is logged with who, when and why | BR-3 |  | Given any approval or rejection, then the log shows the actor, timestamp and reason | Not started

## Test Cases
TC ID | Test case | Proves FR | Result | Last run | Notes
TC-1 | Start a refund on an eligible order | FR-1 | Pass | 2026-10-20
TC-2 | Refund option hidden on orders older than 30 days | FR-1 | Pass | 2026-10-20
TC-3 | Auto-approve a 42 dollar refund | FR-2 | Not run |  | Waiting on finance threshold sign-off
TC-4 | Gateway accepts payout for an approved refund | FR-3 | Fail | 2026-10-22 | Sandbox returns 429 under load

## Lists (hidden)
Priority | Build status | Result
Must | Not started | Not run
Should | In progress | Pass
Could | Built | Fail
Won't | Released